## Josh
Date | User Story | Hours | Description
2025-10-24 | NA | 1 | Team Sprint Meeting
2025-10-27 | NA | 0.1 | Devised the template and skeleton handler for ALL bet-button adding. Since this task applies to 4.3-4.13, I just list it as NA.
2025-10-28 | 4.16 | 0.25 | Fleshed out the add_bet function, which is used to store all bets for final payout computation, so I'll count it towards this user story.
2025-10-28 | NA | 0.1 | Revised button-adding template for ALL bet-button adding. This task is assigned NA for the same reasons as before.
2025-10-30 | 4.16 | 0.75 | Implemented val_bet() and generate_payout() methods, which work together to compute the total payout based on bets.
2025-10-30 | 4.7 | 0.1 | Added and integrated the buttons for triple-number betting.
2025-10-30 | 4.12 | 0.1 | Added and integrated the buttons for thirds betting.
2025-10-30 | 4.2 | 0.1 | Added check to ensure that a user can't bet more chips than they currently possess.
2025-10-31 | 4.18 | 0.25 | Added a leave button to the Roulette GUI, and made sure that all bets were lost if the user quits during a spin.
2025-10-31 | 4.14 | 0.2 | Added a mechanism to prevent further betting while the wheel is spinning.
2025-11-03 | NA | 0.5 | Team Sprint Meeting
2025-11-09 | NA | 5.5 | Wrote the Sprint 2 release, updated the Sprint 2 and initial requirements stack spreadsheets. Drafted the Sprint 3 Requirements Stack, Requirements Artifact, and Architecture Document. Applied prologue and various comments to roulette.py and wheel.py.

## Gavin
Date | User Story | Hours | Description
2025-10-24 | NA | 1 | Team Sprint Meeting
2025-10-27 | 4.1 | 1 | Added Roulette's initial screen and connected the corresponding menu button to switch to it.
2025-10-27 | 4.5 | 0.25 | Added way too many buttons to take care of row bets.
2025-10-27 | 4.8 | 0.25 | Added way too many buttons to take care of row pair bets.
2025-10-28 | 4.14 | 1.5 | Added wheel and created the AnimatedWheel class to make it spin!
2025-10-28 | 4.14 | 1 | Adjusted wheel (and table :¦) so the wheel could spin at a precise randomized value. Also moved some UI elements.
2025-10-31 | 4.3, 4.6, 4.9, 4.10, 4.11, 4.13 | 1 | Added the rest of the buttons pertaining to these user stories. Both the GUI and button connections.
2025-11-03 | NA | 0.5 | Team Sprint Meeting

## Mark
Date | User Story | Hours | Description
2025-10-24 | NA | 1 | Team Sprint Meeting
2025-11-03 | NA | 0.5 | Team Sprint Meeting

## Max
Date | User Story | Hours | Description
2025-10-24 | NA | 1 | Team Sprint Meeting
2025-10-28 | 4.8 | 1 | Adding buttons to take care of pair bets
2025-10-29 | 4.8 | 1 | Adding buttons to take care of pair bets
2025-11-03 | NA | 0.5 | Team Sprint Meeting
2025-11-06 | 4.8 | 0.5 | Adding pair bet buttons for 0/1 0/2 0/3 the right way
2025-11-06 |  | 0.25 | Making sure the user has to place a bet to spin the wheel
2025-11-07 | NA | 2 | Adding bet display button and formatting bets

## Bisshoy
Date | User Story | Hours | Description
2025-10-24 | NA | 1 | Sprint team meeting
2025-10-27 |  | 1.5 | Impemented working buttons and general getting used to the GUI technicalities
2025-10-28 | 4.19 | 1 | Added rules button
2025-11-03 | 4.2 | 0.75 | Implemented sounds for the roullete spinning animation
2025-11-03 | NA | 0.5 | Team Sprint Meeting