## Sheet1
Requirement ID | Description | Story Points | Priority | Sprint No.
1 | Foundation: Casino
1.1 | Reliably track user currency(chips) across all games. | 2 | 54 | 2
1.2 | Remove user from casino if user reaches 0 currency. | 1 | 55 | 3
1.3 | Main menu GUI allowing user to select between different games. | 8 | 1 | 1
1.4 | Traditional card deck will contain 52 standard playing cards (4 suits, 12 ranks) which can be removed from the deck at random. | 3 | 2 | 1
1.5 | The card deck must also have the option of being shuffled, restoring all 52 cards and rerandomizing their order in the deck. | 2 | 3 | 1
2 | Poker as a game option.
2.1 | The GUI for Poker should show the public cards progressively dealt and the chips bet by each player. | 8 | 38 | 3
2.2 | User should be able to specify between 1 to 3 AI opponents. | 3 | 45 | 3
2.3 | AI opponents must start with a random amount of chips. | 1 | 46 | 3
2.4 | Each player must be initially dealt two cards at the beginning of a game. | 2 | 37 | 3
2.5 | The game must track the number of chips each player holds. | 2 | 48 | 3
2.6 | The game flow must begin with three cards being dealt (flop), then one (turn), then one final card (river), with opportunities to bet after each phase. | 3 | 39 | 3
2.7 | AI opponents must have a strategy for deciding when to bet and how much to bet, considering their cards and the public cards dealt. | 13 | 47 | 3
2.8 | The user should be able to bet chips, either matching a current bet or raising the bet, during a round. | 3 | 40 | 3
2.9 | The user should be able to fold, forfeiting their hand and any bet chips during a game. | 3 | 41 | 3
2.1 | The user should be able to immediately bet all their chips during the game, going all in. | 3 | 42 | 3
2.11 | The user should be able to check, doing nothing, during a round. | 3 | 43 | 3
2.12 | After final bets, all remaning (non-folded) hands are ranked based on standard hand precedence, the winner receiving all chips that were bet. | 5 | 44 | 3
2.13 | AI opponents must be removed once they run out of chips. | 2 | 49 | 3
2.14 | The user should be able to exit Poker to the main menu after folding or after a game concludes, leaving with their remaining chips. | 1 | 50 | 3
2.15 | The user should be forcefully exited to the main menu upon losing all chips in Poker. | 1 | 51 | 3
2.16 | Player wins and exits to the main menu if all AI opponents lose all of their chips. | 1 | 52 | 3
2.17 | The rules must be accessible to the user through the interface. | 1 | 53 | 3
3 | Blackjack as a game option.
3.1 | The player must be able allocate an amount from their chips to play, and they must not be immediately sent to the main menu if they spend all their chips. | 2 | 12 | 1
3.2 | The player and dealer entity must be initially dealt two cards from a deck. | 3 | 4 | 1
3.3 | The GUI should display the player's cards as revealed, and all but the first of the dealer's cards as revealed(the other must be hidden). | 8 | 7 | 1
3.4 | The user and dealer should be able to repeatedly hit, obtaining a new card each time. | 3 | 5 | 1
3.5 | The user and dealer should also be able to stand, obtaining no new cards. | 3 | 6 | 1
3.6 | The sum of a hand should be based on values assigned to each card (number = #, face = 10). The ace should be valued at 1 or 11 so that max(sum) <= 21. | 5 | 8 | 1
3.7 | If all of a user's hand's possible sums (considering possible ace values) exceeds 21(busts), the user loses the game. | 2 | 9 | 1
3.8 | The game flow should allow the user to repeatedly hit. Once the user stands, the dealer must reveal the hidden card, and hit until their sum is at least 17. | 3 | 10 | 1
3.9 | If the dealer stands, the player wins if their maxmium possible sum (considering aces) exceeds the dealer's, or if the dealer busts. | 5 | 11 | 1
3.1 | If the player wins, they received double the chips they put up as an initial amount. | 2 | 13 | 1
3.11 | If the player loses, they lose the starting amount. If they lost the last of their chips, they are sent to the main menu. | 2 | 14 | 1
3.12 | The player may exit to the main menu at any time, but if they exit during a game, they forfeit their starting amount. | 2 | 15 | 1
3.13 | The player must have access to the Blackjack rules through an option on the GUI. | 1 | 16 | 1
4 | Roulette as a game option.
4.1 | The GUI must display a European Roulette board and a wheel with slotted numbers from 0-36. | 13 | 17 | 2
4.2 | A user must only bet from their exisiting supply of chips. They do not actually lose their chips at this point. | 2 | 18 | 2
4.3 | A user should be able to place their amount directly on a number, which will guarantee 35x if they win. | 8 | 19 | 2
4.4 | A user should be able to place their amount on a line between two numbers, which will guarantee 17x if they win. | 8 | 20 | 2
4.5 | A user should be able to place their amount at the edge of a three-number row, which will guarantee 11x if they win. | 8 | 21 | 2
4.6 | A user should be able to place their amount on the intersection of four numbers, which will guarantee 11x if they win. | 8 | 23 | 2
4.7 | A user should be able to place their amount on the intersection of three numbers(0, 1, and 2 or 0, 2, and 3), which guarantees 11x if they win. | 8 | 24 | 2
4.8 | A user should be able to place their amount on the edge between two rows, which guarantees 5x if they win. | 8 | 25 | 2
4.9 | A user should be able to place their amount on the red or black box, which guarantees 1x if they win. | 8 | 26 | 2
4.1 | A user should be able to place their amount on the odd or even boxes, which guarantees 1x if they win. | 8 | 27 | 2
4.11 | A user should be able to place their amount on the 1-18 or 19-36 boxes, which guarantees 1x if they win. | 8 | 28 | 2
4.12 | A user should be able to place their amount on the 1st, 2nd, or 3rd 12 boxes, guaranteeing 2x if they win. | 8 | 29 | 2
4.13 | A user should be able to place their amount at the bottom of any number column, guaranteeing 2x if they win. | 8 | 30 | 2
4.14 | When the user finishes betting, the displayed wheel should spin, randomly landing on one of the randomized number slots. | 8 | 31 | 2
4.15 | If the wheel lands on zero, all bets placed on even should be considered to be lost. | 8 | 32 | 2
4.16 | If the user's bet wins based on the wheel, they must be rewarded chips as specified by their bet. | 2 | 33 | 2
4.17 | If the user's bet does not win, they lose the amount the allocated for betting, exiting to the main menu if they run out of chips. | 2 | 34 | 2
4.18 | The user should have the option to leave at any point, with no chip forfeiting like in Blackjack or Poker. | 2 | 35 | 2
4.19 | The user should be shown Roulette instructions if requested. | 1 | 36 | 2
4.2 | The user wants sounds effect to feel more engaged. | 2 | BONUS ADDITION | 2
4.21 | The user should be able to review what bets they have placed so that they can keep track of what they've bet chips on. | 3 | BONUS ADDITION | 2
5 | Sabacc
5.1 | The GUI for Sabaac will show the player's cards faceup, the cards of the other players facedown, the dice, and the number of chips contained in the Sabaac pot. | 8 | 56 | 4
5.2 | The GUI should display the discard pile, or an empty space if the discard pile is empty, and the chip values that have been bet for each game. | 8 | 57 | 4
5.3 | The player should be able to choose between 1 and 3 AI opponents. | 5 | 58 | 4
5.4 | The card deck for Sabaac will consist of 62 cards, 30 positive and 30 negative, from values 1 to 10, with 3 of each corresponding to the suite, and two 0 cards. | 5 | 59 | 3
5.5 | The GUI should show the positive cards as green, the negative cards as red, 0 cards as any color, and the different suites as represented by a circle, triangle, or square. | 3 | 60 | 4
5.6 | To begin a game of sabaac, the player and every AI opponent must "buy in" and these chips will go to the sabaac pot. | 5 | 61 | 4
5.7 | The value in the sabaac pot should be randomized between accesses to the Sabacc mode and between games to simulate activity. | 2 | 62 | 4
5.8 | At the beginning of the game, all players should be dealt 2 cards, and another card should be dealt and displayed faceup representing the discard pile. | 5 | 63 | 3
5.9 | A game of sabacc should proceed through three rounds, in which users are given the opportunity to draw, swap, stand, or junk. | 8 | 64 | 3
5.1 | In each round, the order of play should remain the same, and the user should play last. | 3 | 65 | 4
5.11 | When a player draws, a card should be dealt and added to their hand, and the player should be able to optionally add a card to the discard pile. | 5 | 66 | 3
5.12 | When a player swaps, they may choose a card from their hand and swap it with the card at the top of the discard pile | 5 | 67 | 3
5.13 | When a player stands, they finish their turn without changing their hand. | 2 | 68 | 3
5.14 | When a player junks, all of their cards go to the discard pile and they are out of the game, forfitting any chips bet. | 3 | 69 | 3
5.15 | At the end of each round, the AI opponents should be able place a bet based on the quality of their hand, either matching a current bet or raising it. | 8 | 70 | 4
5.16 | AI opponents must initialize with a randomly generated chip balance. | 3 | 71 | 4
5.17 | Each player's chip balance should be tracked. | 1 | 72 | 3
5.18 | The user should be able to bet chips, either matching a current bet or raising the bet, during a round. | 8 | 73 | 3
5.19 | After each round, there should be functionality for rolling 2 six sided dice, and the result should be displayed by the GUI. | 5 | 74 | 3
5.2 | If the result of the 2 dice roll is doubles, players must discard all of their cards and redraw a new hand equal in card number size to their previous hand. | 5 | 75 | 3
5.21 | At the end of the final round, the winner should be determined by adding the card values in a players hand together, and comparing them against each other. | 5 | 76 | 3
5.22 | The player closest to 0 wins. If two players are the same numeric distance away, the player with the closest positive value is the winner. | 2 | 77 | 3
5.23 | If there is still a tie or more than one player gets 0, the hand with more cards wins. | 2 | 78 | 3
5.24 | The winning player should have the chips from the bets after each round added to their casino total. | 2 | 79 | 3
5.25 | If the winning player wins on a "sabaac" which is when they have a final value of 0, the sabaac pot should be emptied and the chips held should be added to the player. | 3 | 80 | 3
5.26 | After each game, the player should have the option to play again, or leave to return to the Casino. | 2 | 81 | 4
5.27 | Losing players forfit all chips bet during the game. Once a player reaches a chip amount of zero, they are removed from the game(menu in case of the user) | 3 | 82 | 4
5.28 | The player is exited to the main menu with all won chips once all AI opponents are removed. | 2 | 83 | 4
5.29 | The player should be met with genre-appropriate background music whilst playing sabacc. | 3 | BONUS ADDITION | 3