## Sheet1
2 | Poker as a game option.
2.1 | The GUI for Poker should show the public cards progressively dealt and the chips bet by each player. | 8 | 38 | 3
2.2 | User should be able to specify between 1 to 3 AI opponents. | 3 | 45 | 3
2.3 | AI opponents must start with a random amount of chips. | 1 | 46 | 3
2.4 | Each player must be initially dealt two cards at the beginning of a game. | 2 | 37 | 3
2.5 | The game must track the number of chips each player holds. | 2 | 48 | 3
2.6 | The game flow must begin with three cards being dealt (flop), then one (turn), then one final card (river), with opportunities to bet after each phase. | 3 | 39 | 3
2.7 | AI opponents must have a strategy for deciding when to bet and how much to bet, considering their cards and the public cards dealt. | 13 | 47 | 3
2.8 | The user should be able to bet chips, either matching a current bet or raising the bet, during a round. | 3 | 40 | 3
2.9 | The user should be able to fold, forfeiting their hand and any bet chips during a game. | 3 | 41 | 3
2.1 | The user should be able to immediately bet all their chips during the game, going all in. | 3 | 42 | 3
2.11 | The user should be able to check, doing nothing, during a round. | 3 | 43 | 3
2.12 | After final bets, all remaning (non-folded) hands are ranked based on standard hand precedence, the winner receiving all chips that were bet. | 5 | 44 | 3
2.13 | AI opponents must be removed once they run out of chips. | 2 | 49 | 3
2.14 | The user should be able to exit Poker to the main menu after folding or after a game concludes, leaving with their remaining chips. | 1 | 50 | 3
2.15 | The user should be forcefully exited to the main menu upon losing all chips in Poker. | 1 | 51 | 3
2.16 | Player wins and exits to the main menu if all AI opponents lose all of their chips. | 1 | 52 | 3
2.17 | The rules must be accessible to the user through the interface. | 1 | 53 | 3
5 | Sabacc | 0
5.4 | The card deck for Sabaac will consist of 62 cards, 30 positive and 30 negative, from values 1 to 10, with 3 of each corresponding to the suite, and two 0 cards. | 5 | 59 | 3
5.8 | At the beginning of the game, all players should be dealt 2 cards, and another card should be dealt and displayed faceup representing the discard pile. | 5 | 63 | 3
5.9 | A game of sabacc should proceed through three rounds, in which users are given the opportunity to draw, swap, stand, or junk. | 8 | 64 | 3
5.11 | When a player draws, a card should be dealt and added to their hand, and the player should be able to optionally add a card to the discard pile. | 5 | 66 | 3
5.12 | When a player swaps, they may choose a card from their hand and swap it with the card at the top of the discard pile | 5 | 67 | 3
5.13 | When a player stands, they finish their turn without changing their hand. | 2 | 68 | 3
5.14 | When a player junks, all of their cards go to the discard pile and they are out of the game, forfitting any chips bet. | 3 | 69 | 3
5.17 | Each player's chip balance should be tracked. | 1 | 72 | 3
5.18 | The user should be able to bet chips, either matching a current bet or raising the bet, during a round. | 8 | 73 | 3
5.19 | After each round, there should be functionality for rolling 2 six sided dice, and the result should be displayed by the GUI. | 5 | 74 | 3
5.2 | If the result of the 2 dice roll is doubles, players must discard all of their cards and redraw a new hand equal in card number size to their previous hand. | 5 | 75 | 3
5.21 | At the end of the final round, the winner should be determined by adding the card values in a players hand together, and comparing them against each other. | 5 | 76 | 3
5.22 | The player closest to 0 wins. If two players are the same numeric distance away, the player with the closest positive value is the winner. | 2 | 77 | 3
5.23 | If there is still a tie or more than one player gets 0, the hand with more cards wins. | 2 | 78 | 3
5.24 | The winning player should have the chips from the bets after each round added to their casino total. | 2 | 79 | 3
5.25 | If the winning player wins on a "sabaac" which is when they have a final value of 0, the sabaac pot should be emptied and the chips held should be added to the player. | 3 | 80 | 3
1 | Foundation: Casino | 0 | 0
1.2 | Remove user from casino if user reaches 0 currency. | 1 | 55 | 3
122
BONUS REQUIREMENTS IF TIME PERMITS
5.1 | The GUI for Sabaac will show the player's cards faceup, the cards of the other players facedown, the dice, and the number of chips contained in the Sabaac pot. | 8 | 56 | 3
5.2 | The GUI should display the discard pile, or an empty space if the discard pile is empty, and the chip values that have been bet for each game. | 8 | 57 | 3
5.3 | The player should be able to choose between 1 and 3 AI opponents. | 5 | 58 | 3
5.5 | The GUI should show the positive cards as green, the negative cards as red, 0 cards as any color, and the different suites as represented by a circle, triangle, or square. | 3 | 60 | 3
5.6 | To begin a game of sabaac, the player and every AI opponent must "buy in" and these chips will go to the sabaac pot. | 5 | 61 | 3
5.7 | The value in the sabaac pot should be randomized between accesses to the Sabacc mode and between games to simulate activity. | 2 | 62 | 3
5.1 | In each round, the order of play should remain the same, and the user should play last. | 3 | 65 | 3
5.15 | At the end of each round, the AI opponents should be able place a bet based on the quality of their hand, either matching a current bet or raising it. | 8 | 70 | 3
5.16 | AI opponents must initialize with a randomly generated chip balance. | 3 | 71 | 3
5.26 | After each game, the player should have the option to play again, or leave to return to the Casino. | 2 | 81 | 3
5.27 | Losing players forfit all chips bet during the game. Once a player reaches a chip amount of zero, they are removed from the game(menu in case of the user) | 3 | 82 | 3
5.28 | The player is exited to the main menu with all won chips once all AI opponents are removed. | 2 | 83 | 3
5.29 | The player should be met with genre-appropriate background music whilst playing sabacc. | 3 | 84 | 3
55
177